## Slide 1: Aim of the scrubbing
Reduction of the SEY to allow for operation with 75 and possibly 50 ns beams with no significant pressure rise, acceptable heat load and minimum blow-up
According to the results of the scrubbing allow fast ramp-up with 75 or possibly 50 ns beams up to 900 – 1400 bunches in steps of 100-200 bunches per step (see Chamonix)
Allow early detection of issues for high intensity operation (RF, UFOs, etc.)

## Slide 2: Scrubbing run requirements
Requirements for the scrubbing run:
  In the injectors:
    50 ns beam with up to 1.5x1011 p/bunch with emittances in the range 2-3.5 mm
    25 ns beam with 1.15x1011 p/bunch with nominal emittance
  In the LHC:
    Injection of 144 bunches with 50 (25) ns spacing (up to nominal transverse emittance)
    Machine protection set-up for high intensity at 450 GeV/c (for > 2000 bunches)
    RF should be conditioned for operation at high intensity
    Transverse feedback set-up for high intensity operation with 50 and 25 ns beams
During the scrubbing run:
    Solenoids (experimental and anti e-cloud) and experimental dipoles should be OFF
    Vacuum interlock levels should be temporarily increased to 2x10-6 mbar (from 5x10-7 mbar?) where and if needed and compatibly with machine and experiment protection requirements
    Cryo valve regulation for the beam screen in relaxed mode? Valves regulating when T> xx K?

## Slide 3: Day 0
  During the injection tests with 50 ns beam:
  Injection of four pairs of trains of 36 bunches with variable spacing to try and constrain the parameters at the beginning of the scrubbing.
  Proposed spacings among the two trains of 36 bunches:
    225 ns
    1000 ns
    2000 ns
    4000 ns
  Detailed filling scheme to be defined  Elias

## Slide 4: Day 1-3
Inject trains of up to 4x36 bunches (1.3-1.5x1011 p/bunch) with 50 ns spacing with nominal emittance up to >1000 bunches compatibly with vacuum rise, heat loads and beam stability.
  Injection of trains of 36 bunches from the SPS and nominal spacing in the LHC (975 ns – i.e. 38 empty 25 ns slots)
    Monitoring of the temperature of the beam screens and RF stable phase (µ energy loss) as well as vacuum evolution to follow-up the scrubbing progress
  Once filled the whole machine dump and go to the next step: injection of nx36 bunches from SPS and nominal spacing in the LHC (n=2,3,4)
  Filling schemes to be defined in advance (constraint: we will need to inject 12 bunches to start. Do we leave the pilot in to start to avoid loss of time?)
  Try and reduce bunch-length to enhance scrubbing

## Slide 5: Day 4
Evaluation of the sensitivity to orbit distortion and radial position at 450 GeV/c
  Introduce a peak-to-peak orbit distortion of ±0.5 mm (what is acceptable?
  Introduce a radial position error of ±0.5×10-3 (what is acceptable?)
Ramp/squeeze/collision with 50 ns beams (same number of bunches as achieved with 75 ns if compatible with vacuum). For the ramp vacuum interlock levels will be restored to nominal settings.
Inject one beam with separation bumps and crossing angles OFF

## Slide 6: Day 5-7
Inject trains of up to 2x72 bunches (nominal) with 25 ns spacing with nominal emittance up to >2000 bunches compatibly with vacuum rise, heat loads and beam stability.
  Injection of trains of 48 bunches from the SPS and nominal spacing in the LHC (975 ns – i.e. 38 empty 25 ns slots)
    Monitoring of the temperature of the beam screens and RF stable phase (µ energy loss) as well as vacuum evolution to follow-up the scrubbing progress
  Once filled the whole machine got to the next step: injection of nx48 bunches from SPS and nominal spacing in the LHC (n=2,3)
  Filling schemes to be defined in advance (constraint: we will need to inject 12 bunches to start. Do we leave the pilot in to start to avoid loss of time?)
  Try and reduce bunch-length to enhance scrubbing

## Slide 7: Day 8
Ramp/squeeze/collision with 50 ns beams (same number of bunches as achieved with 75 ns if compatible with vacuum). For the ramp vacuum interlock levels will be restored to nominal settings.
  Measurement of the pressure rise for the filling pattern ised on day 0 to benchmark code and determine effect on SEY and reflectivity.
Decision on starting physics with 75 or 50 ns with fast ramp-up in intensity to 900 or 1400 bunches based on the result of the scrubbing.
Criteria for the decision to progress with 75 or 50 ns:
  Go for 50 ns if scrubbing has occurred with 25 ns spacing
  Go for 50 ns if pressures after injection of ~1400 bunches with 50 ns spacing are in the range of 10-8 mbar or lower
  Else go with 75 ns

## Slide 8: Measurements
  Emittance along the trains  ? + Federico
  Tune shift along the bunch train with Schottky  Tatiana +
  Stable phase  Walter + Giulia
  BBQ  ?
  HeadTail monitor  Benoit?
  Heat load  Walter + Cryo
  Vacuum pressures  Vacuum team
  Bunch-by-bunch position  Dedicated monitor available? Who is responsible in ABP?
  Lifetime of the bunches along the train  Giulia? + ….